## Sheet1
Feature | user stories | planned sprints | Estimated hours | assignation
create account | user will open the app and the app will ask the user for permissions (inculdes location) then the user will sign up (using facebook, google etc) or normal signing up (filling email and phone number) / | 2 | 10 | team 1
| 2 user will get OPT to confirm that he is the user / | 1 | 5 | team 1
| 3 finish signing in / | 1 | 2 | team 1
| 4 login | 1 | 2 | team 1
create account for resturant | as resturant the resturant owner should create account and fill the information about it and upload the menu and it's prices and the location | 1 | 5 | team 1
view resturants | user will check the avaliable resturants based on his location | 1 | 5 | team 1
| user should find resturants based on categories | 1 | 3 | team 1
Search Restaurants | user will type the resturant name or check the resturants categories | 1 | 4 | team 2
View Menu | after selecting the resutrant the user should find the prices of the food and description | 1 | 3 | team 2
Add to Cart | user should select from the menu the desired food then check out | 1 | 5 | team 2
Purchase | user will select the location if it's the default or new location based on location access and then add promo if there's any and select payment method | 1 | 2 | team 2
Restaurant views order | once user finished the resturant should get notification about the order address and phone number and user name and the payment method | 1 | 2 | team 2
Restaurant marks order as delivered | once the delivery contacts the user and find him then deliver and the user pays the delivery man should mark it as delivered | 2 | 6 | team 2